BSSE FINAL YEAR PROJECT

STUDENTS HANDBOOK

VERSION 5.1

Faculty of Computing

Riphah International University

Table of Contents:

| 01. | Glossary |  |  | 03 |
| --- | --- | --- | --- | --- |
| 02. | Introduction |  |  | 04 |
|  | 2.1. | Focus |  | 05 |
|  | 2.2. | Importance of Final Year Project |  | 06 |
| 03. | Selecting Your Project & Team Members |  |  | 07 |
|  | 3.1 | Project Team |  | 07 |
|  | 3.2 | Choosing Your Project & Supervisor |  | 07 |
|  | 3.3 | Finalizing Project Proposal |  | 08 |
| 04. | Literature / Markey Survey |  |  | 10 |
| 05. | Documentation |  |  | 12 |
|  | 5.1 | Project Report |  | 12 |
|  | 5.2 | A Very Short Guide to Good Writing |  | 14 |
|  | 5.3 | Giving Presentations |  | 16 |
| 06. | Project Assessment |  |  | 18 |
| 07. | Schedule & Milestones |  |  | 20 |
| 08. | Policies |  |  | 21 |
| 09. | Responsibilities of Project Students |  |  | 23 |
| 10. | Appendices |  |  | 25 |

1. Glossary

| FYP: | Final Year Project (Also known as Final Year Project) |
| --- | --- |
| FYP | Final Year Project |
| BSSE: | Bachelor of Science in Software Engineering |
| FC: | Faculty of Computing, Riphah International University |
| RIPHAH: | Riphah International University |
| Faculty: | Fulltime permanent faculty member |
| Supervisor: | A fulltime faculty member of FC responsible for the supervision of FYP. |
| Exam Committee: | A group of faculty members responsible for evaluating and grading projects. |
| Coordinator: | A faculty member appointed by FC to coordinate the FYP tasks |
| Student: | A student registered for FYP in FC |
| Group/Team: | A group of students formed as a team to work on the FYP. |

2. Introduction

The Final Year Project (FYP) provides you with an opportunity to apply the principles learned in different courses, and integrate material learned at different stages of your BSSE degree program. There may also be a need for additional, domain specific knowledge in a project, which will necessitate additional study.

Learning Outcome: On successful completion of the project, you should be able to apply your knowledge and understanding of software engineering to analyzing problems, creating and evaluating solutions, and critically assessing your own work. You should also be able to prepare project plans, give presentations, and write reports.

Learning Method: FYP is a self-learning exercise, under the guidance of project supervisor. The following six learning elements form the basis of a project: knowledge, understanding, applying, analyzing, evaluating, and creating.

During the project you are expected to:

- Develop an understanding of the technical knowledge on which your project is based.

- Analyze a problem.

- Create a solution (Synthesis).

- Apply your knowledge and understanding in executing the project.

- Evaluate your work.

Assessment

- Semester 1: Interim Report and Prototype

- Semester 2: Final Report, Presentation, and Developed System

2.1. Focus

The objective of FYP is to develop a system that meets a set of user needs. This may take many forms, for example: an application, a server, a program, a library, a collection of programs, an embedded system, a hardware-software system, plug-ins, extensions, modifications to existing software, etc.

You should focus on following sound software engineering principles and evaluating your work thoroughly.  You will do background research into both the technology and the marketplace. You must test your software to make sure it works correctly.

FYPs are based on the principles of quality software development, which can be summarized as follows:

- Understand what is needed

- Design a solution

- Design and implement a system to realize the solution

- Verify that the implementation matches the design

- Validate that the implementation correctly realizes solution

- Evaluate how well the solution solves the problem

The developed system and final report will be the main output of the project, which should show that your system is of suitable quality and solves user needs.

2.2. Importance of Final Year Project

You will continue to gain experience after you graduate, but FYP will be your first exposure to a significant software engineering project. It is essential that you learn from this exposure and practice all the methodologies involved. It is also important that you learn not just how to apply what you know, but also to apply it with judgment, with the ability to assess what you are doing and to be critical of it.

You should keep in mind that:

- It is the largest single piece of work you will do during your degree course.

- It is the part of the curriculum that allows you to specialize in a topic you are good at or enjoy.

- It is the part of your degree program that prospective employers will most likely ask you about at an interview.

- It allows you to show off a wide range of skills and knowledge learned during your course.

- It encourages integration of material learned in several courses.

Responsibility: It is important to note that you are responsible for the success of your project. Your supervisor is only supposed to provide you with guidance and feedback – you must not rely on your supervisor as if he/she is your project manager or team lead. It is also your responsibility to keep record and submit the monthly attendance status of the meeting held with the supervisor, with supervisor’s consent (Template-08).

3. Selecting Your Project & Team Members

3.1. Project Team

For FYP, a project team consisting of 3 students is encouraged; however, a group of 2, 4 or 5 can be formed only if the scope and complexity of the project justifies these numbers.

Use “Template-01” to fill in the details of project team members and submit hard copy to Project Coordinator before the end of first week (1st Semester).

3.2. Choosing Your Project & Supervisor

Given that you are going to spend a lot of time working on your project, it is essential that you pick a project which you like and which you can do. Note that these are not necessarily the same things: just because you like a project doesn’t mean you are qualified to do it. You may not have taken all the requisite courses or it may be a more theoretically-aligned project whereas you might be a more practically-oriented student (or vice versa). Think long and hard before making your final choice. At the very least, you should take the following steps in assessing and choosing a project.

- Find out what are your options.

- Make a list consisting of at-least three projects.

- Write a brief description of each project

- Go and talk to faculty members you wish to supervise you during the project. Discuss your ideas in detail and take notes. It is important that you demonstrate your interest and necessary knowledge about the projects to convince a faculty member of your choice to supervise you.

Once you have finalized your project & supervisor use “Template-02” to write down initial proposal and submit hard copy to project coordinator before the end of second week (1st Semester).

3.3. Finalizing Project Proposal

You will need to further refine your project proposal and present it to the entire faculty in fourth week of the semester (1st Semester). Faculty members will evaluate your proposal for scope, complexity, originality of idea (creativity) and amount of self-learning involved. Faculty members will provide feedback on your proposal, which you will need to incorporate in your project scope in consultation with your project supervisor. Faculty members can also reject a proposal if you fail to effectively present scope, complexity, originality of idea (creativity) and amount of self-learning involved.

Use “Template-03” to create project proposal presentation. You will need to submit soft copy (PDF Format) of your presentation to project coordinator before the end of fourth week (1st Semester).

After the proposal presentation you will need to finalize your project proposal (including initial plan) in consultation with project supervisor.

Use “Template-04” to create final project proposal and submit both hard copy (signed by project supervisor) and soft copy (PDF Format) to project coordinator before the end of sixth week (1st Semester).

Your final project proposal should consist of:

- Full Name & Designation of Project Supervisor

- Opportunity & Stakeholders: Briefly introduce opportunity and the stakeholders for which software system is being developed.

- Existing System: Description of the existing system and current situation

- Problem Statement: Describe the motivation for new solution.

- Proposed Solution

- Scope of the Project: Discuss major modules in this section.

- List of Faculty Proposed Changes

- Work Breakdown Structure: A work breakdown structure (WBS) is deliverable based decomposition of project scope. The WBS includes 100% of the work defined by the project scope and captures all deliverables – in terms of the work to be completed, including project management.

- Roles & Responsibility Matrix: The purpose of roles & responsibility matrix is to identify who will do what. You will need to list items in WBS and identify activities needed to complete each deliverable. You will then identify which team member(s) will be responsible for completing which activity and how long it should take.

At this stage you are only finalizing project proposal, therefore your project plan (“Work Breakdown Structure” and “Roles & Responsibility Matrix”) can be based on rough estimates. You must regularly refine both “Work Breakdown Structure” and “Roles & Responsibility Matrix” as you elicit more requirements during your project.

A critical factor that will determine quality and success of FYP is your ability to manage time. Final Year Projects are completely different from smaller projects you may have undertaken. This project will require a considerable amount of your time: approximately 240+ hours / person.

Begin your project early, work consistently at it, and track your progress. Your project plan helps you to think about all the things you need to do, their inter-relationships, and the time each will take.

4. Literature / Market Survey

Ideally you should conduct literature / market survey for problem identification. However even after you have defended your project proposal, you must conduct detailed literature / market survey to gain more insight about the problem you are trying to solve. This is an essential step that will help you become an expert in the problem at hand: a problem-domain expert.

- It shows that you not only understand what you want to do, but you understand what others have done related to your project. If you can tell people about what has already been done and what methods already exist, then your readers will think that at least you are interested in your topic, have some self-initiative and are informed and up-to-date.

- It shows that you are intelligent enough to evaluate the quality of the other work done on the subject, i.e., it shows that you are capable of thinking critically and identifying strengths and weakness.

- It gives you opportunity to tell how your project is related to previous work done by others on the subject.

- It tells the reader if you are simply going to duplicate others’ work for the sake of gaining a better understanding, improve upon others’ work or perhaps combine the methodology of two or more existing approaches to solving a problem.

The only way to become an expert in both the problem domain and the solution domain is to learn as much as possible about the area and to learn it as quickly and efficiently as possible.

Go online and search for articles, books and papers related to your subject. Be creative and persistent in your keyword search until you hunt down good references or examples.

- When you read some literature that you think is useful and related, first record the citation on your list of references, using IEEE format.

- When you read some literature that is not very useful, do not include it on your list of references. More references do not mean a better list of references. Useless references only confuse a careful reader and make you lose credibility.

- In each document, identify the approach(es) / method(s) for solving problem(s), and compare this/these with what you already know.

- Identify which approaches and/or methods you will use and omit in your project.

- After you feel satisfied that you know all or most of the existing approaches/methods, list out all the approaches/methods, in a logical sequence (perhaps in chronological order).

- For each approach/method: describe how it works and what its components are; mention its strengths and/or weaknesses; tell if you will use or omit the approach for your project and why or why not.

Finally, it is very important that you realize that, to fully understand anything that you read, you must write it up in your own words. If you can’t express or speak about a given idea, then you haven’t truly understood it in any useful way.

5. Documentation

Writing is an essential part of understanding. In case of documentation, writing is essential for others to understand what you have done. There are two reasons why you want others to understand your work:

- So that you can be given credit for it (your marks depend on it);

- So that others can carry on your work and develop or maintain your system.

The best way to organize your writing is to keep a log book of all work in progress. You should go out and buy a nice hard-cover notebook and write everything you do on the project into this log book every day. Every thought and observation you have on your project should go into this book, along with notes of meetings with your supervisor, results, theoretical developments, calculations, everything. This log book will become an invaluable source of material when you come to write up your project in the final report.

5.1. Project Report

Your project report is a critical part of your project. It defines what you have done and why you have done it. It is also one of the main outputs on which your project will be examined and graded.

Your final year project provides you with an opportunity to demonstrate your ability to use your judgment. This means that you must show your skill at assimilating (to incorporate, understand), synthesizing (to produce, blend) and critically appraising (to critically evaluate) all material relevant to the project.

Your main opportunity to display your talents at assimilation and synthesis comes when you describe the background material you read, the requirements, specification, and design phases of your work. Needless to say, synthesis means that you must write the text yourself, expressing your understanding of the material in your own words.

Resist the temptation, no matter how strong, to copy sentences or paragraphs (or whole sections) from other books or articles. Copying is not synthesis and it demonstrates neither your assimilation of material nor your understanding of it. If you do come across a sentence or paragraph which is so good that it must be used, then do so and include it as a direct quotation, providing a reference to the original source.

It is extremely important that you also appraise, or assess, your work critically, i.e. with objectivity and with a view to seeing how it could be improved. Such honest criticism does not mean you will receive fewer marks; in fact, it is likely that you will receive more. Typically, you exercise your talents of critical appraisal at the end of the report in “conclusion and outlook” chapter (Chapter 7) but you can also exercise it throughout the report wherever it seems appropriate. Note that this exercise of critical appraisal is different from the testing processes of verification, validation, and evaluation, which refer to the functionality of the system you have designed. The critique you write applies less to the system and more to the overall objectives, methodologies, and findings of the project.

The structure of your report is critical to the impact you make in your writing. Remember that you are trying to convey a message to the reader and, since this message is likely to be quite complicated, you must assist him or her by making your points clearly and in a logical order.

Because all engineering projects involve (or should involve) the exercise of a fairly standard engineering methodology (requirements, specification, modeling, realization, testing & evaluation), you can, if you wish, adopt a fairly standard structure. However, that this does not mean that you just simply have to fill in the gaps in a general report template (Template-05): this standard structure simply provides you with a place to start as you begin to design the final structure and content of your report. You will still have to do quite a lot of work to make it fit your own project.

5.2. A Very Short Guide to Good Writing

Good writing is difficult. It takes practice and a willingness to revise your work, many times. The goal of writing is to convey a message to the reader. However, writing, and reading, is sequential processes. Therefore, you must construct the meaning of your message, piece by piece, in a linear time-line. However, the meaning you intend to convey may emerge from many sources, not all related in a nice orderly fashion. This creates a problem for the writer: how to order the messages contained in each sentence effectively. The job of a writer is to make the sequence of pieces as mutually-relevant as possible so that the story or message builds naturally, each piece adding to the previous one. When the pieces are presented out of order the impact on the reader is lessened. And remember the golden rule in writing: keep it simple.

The following are some pointers to help you in your task:

- Use short sentences and make sure the sentences are complete.

- Good writing strikes a balance between short sentences and longer more descriptive ones. Just as in oral communication, the full stops mean pauses: too many pauses and the text sounds disconnected, too few and it can be hard to follow the story line. Strike a balance but favour brevity over complexity.

- If you use pictures and diagrams (and you should), make sure each one has a self-contained explanatory caption. Never refer to a picture or diagram in the main text without saying what it is. For example, never say “Figure 2.3 shows the results of the noise test” and then carry on to another topic. Help the reader. Summarize the content of the figure in a short sentence: “Figure 2.3 shows the results of the noise test which demonstrate the robustness of the system to Gaussian noise with a standard deviation of 2.3 or less.” If you have copied the figure from a book or article you must cite the source.

- Make the paragraph your unit of construction. Each paragraph should bind one or more sentences about a given subject or idea. If the subject or idea changes, start a new paragraph.

- Omit needless words. Unnecessary words distract the reader. Don’t write, “This is a system the performance of which is very useful”. Instead, write, “This is a useful system”.

- Write in a way that comes naturally. Speak the sentence. If it sounds correct, trust your ear and use the sentence. If it sounds unnatural, rewrite it.

- Avoid fancy words; they don’t impress anyone.

- Be clear in your expression. If the idea you are trying to convey is getting lost in a sea of words and phrases, draw a line through the sentence and start again.

- Don’t take short-cuts. Explain what you mean. Don’t leave the reader to struggle trying to figure out what is the real meaning of your carefully constructed but concentrated sentence. He may conclude there is none. Explain all acronyms the first time you use them.

- Revise and rewrite. It is highly unlikely that you will manage to find the best way of expressing an idea with your first attempt. Nonetheless, make that attempt and then be prepared to revise it, again and again.

Remember, if you want to learn how to write a good report, you need to do two things: you need to read other good reports and you need to practice your own writing.

5.3. Giving Presentations

During the course of your project, you will be required to give several presentations:

- Proposal presentation to entire faculty in 4th week of your first semester. (Use Template-03)

- Progress presentation with your prototype demo to Exam Committee in week immediately after finals of your first semester. (Use Template-07)

- Final presentation along with your demo to Exam Committee in 14th week of second semester. (Use Template-06)

Important Requirement:

- All project deliverables (e.g., Presentations, Reports, Software System, etc.) should be reviewed by supervisors at-least once before submission/presentation.

- You must state in your presentations, whether deliverables (including your presentation) were reviewed by your supervisor or not.

You have learned much about presentation skills during your degree program and it wouldn’t be appropriate to attempt to review everything you have been taught already. However, a few pointers may help you give a professional and impressive presentation:

- Don’t depend too much on PowerPoint slides: your speech is the presentation and the slides support you (not the other way around).

- Take your time: pause frequently. Sometimes, the best thing to say is nothing. Short one-second rests create dramatic impact and also give your audience time to assimilate what you’ve said. Of course, you also have to maintain continuity and flow; otherwise people forget what you are talking about. It’s a question of balance.

- Arrive early and make sure you know where all the equipment is. Know how to use it.

- Look at the audience, not at your slides.

- Project your voice (but don’t shout).

- Smile: enjoy giving your presentation.

- Be confident: you’ve done some great work - here is your opportunity to get credit for it.

- The people in the audience are on your side (though sometimes they disguise it well!) They want you to succeed. If they ask you a question you don’t understand, say so and ask their help. Ask them to explain and ask nicely. If you still don’t understand, don’t bluff. Admit your ignorance and suggest ways of how you will overcome that lack of knowledge.

6. Project Assessment

6.1. Final Year Project (Part I)

You are required to participate in the Open House (15th Week of first semester) and showcase your Project Idea, Prototype, and Project Report. Failure to participate will earn you “F” grade unless you have prior approval from both your supervisor and project coordinator.

In the week immediately after finals you will make Progress Presentation (you will also show first five chapters of your report and your working prototype) to FYP Evaluation Committee.  FYP Evaluation committee will evaluate your progress according to the following criteria:

Part-I Evaluation Rubric

| FYP-LO | Below Average | Average | Good (70%) | Excellent (80%) | Outstanding (100%) | Obtained Marks |
| --- | --- | --- | --- | --- | --- | --- |
| FYP-LO1:Marks(10): Demonstrate knowledge of mathematics, science, and software engineering fundamentals and processes. | Poor understanding of basic software engineering concepts. (0-4 Marks) | Understanding of basic software engineering is satisfactory. (5 Marks) | Good understanding of basic software engineering. (7 Marks) | Excellent understanding of basic software engineering. (8 Marks) | Outstanding understanding of basic software engineering. (10 Marks) |  |
| FYP-LO2:Marks(20): Analyze a problem, identify and define software requirements appropriate to its solution. | Lack of appropriate requirements and Market survey is not aligned to project scope. (0-8 Marks) | Requirements are partially aligned with project scope and market survey is aligned to project scope. (10 Marks) | Requirements are gathered through appropriate elicitation techniques and market survey is aligned to project scope. (14 Marks) | Excellent requirement elicitation techniques and market survey is aligned to project scope. (16 Marks) | Outstanding requirement elicitation techniques market survey is 100% aligned to project scope. (20 Marks) |  |
| FYP-LO3:Marks(20): Design and implement software engineering solutions for complex problems, components or processes to meet desired needs. | Designs, plans and proposed project is not according to requirements. (0-8 Marks) | Designs, plans and proposed project is alligened with the requirements. (10 Marks) | Designs, plans and proposed project is good and alligened with the requirements. (14 Marks) | Excellent Designs, plans and proposed project is according to requirements. (16 Marks) | Outstanding Designs, plans and proposed project is according to requirements. (20 Marks) |  |
| FYP-LO4:Marks(10): Evaluate a software engineering solution in a methodical way design and, conduct experiments, analyze and interpret experimental data, and synthesize information to derive valid conclusions. | Software Quality Engineering and GUI standards are poorly applied. (0-4 Marks) | Software Quality Engineering and GUI standards implementation is satisfactory. (5 Marks) | Software Quality Engineering and GUI standards applied are good. (7 Marks) | Software Quality Engineering and GUI standards are excellentlty applied. (8 Marks) | Software Quality Engineering and GUI standards are ourstandingly applied. (10 Marks) |  |
| FYP-LO5:Marks(10) : Apply appropriate techniques, resources, and modern software engineering tools to solve complex problems. | Poor techniques and no appropriate tools are used. (0-4 Marks) | Techniques are partially satisfactory but no tools are used. (5 Marks) | Good techniques are applied and tools are not appropriate. (7 Marks) | Techniques and tools are used excellently. (8 Marks) | Techniques and tools are used outstandingly. (10 Marks) |  |
| FYP-LO6:Marks(10): Work effectively in a team to accomplish a goal. | Poor team work. (0-4 Marks) | Team Work is satisfactory. (5 Marks) | Good team work. (7 Marks) | Excellent team work. (8 Marks) | Outstanding team working. (10 Marks) |  |
| FYP-LO7:Marks(10): Communicate effectively on complex engineering activities and make effective presentations. | Poor communication skills. (0-4 Marks) | Communication skills are satisfactorry. (5 Marks) | Good communication skills. (7 Marks) | Excellent communication skills. (8 Marks) | Outstanding communication skills. (10 Marks) |  |
| FYP-LO8:Marks(10): Demonstrate knowledge of project management principles and techniques. | Poor knowledge of project management principles and techniques. (0-4 Marks) | Knowledge of project management principles and techniques is satisfactory. (5 Marks) | Good knowledge of project management principles and techniques. (7 Marks) | Excellent knowledge of project management principles and techniques. (8 Marks) | Outstanding knowledge of project management principles and techniques. (10 Marks) |  |

Evaluation Method:

- 50% by Exam Committee Average + 50% by Supervisor

- Supervisor may evaluate each member of the project group individually

- Decision of the Exam Committee and Supervisor will be final.

For Example:

- Average Marks by Faculty for the Group: 68 (34 %)

- Supervisor Marks for Student 1: 76 (38%)

- Supervisor Marks for Student 2: 60 (30%)

- Supervisor Marks for Student 3: 92 (46%)

- Student 1 Grade: 34+38 = 72% (B Grade)

- Student 2 Grade: 34+30 = 64% (C Grade)

- Student 3 Grade: 34+46 = 80% (A Grade)

6.2. Final Year Project (Part II)

In 14th week of the semester, FYP Evaluation Committee and your Supervisor will grade you based on your final report, presentation, and demonstration.

FYP Evaluation Committee will evaluate you based upon difficulty level (scope, complexity, creativity and amount of self-learning involved in developing the final system) and quality (presentation, usability, system design, documentation, and coding). The following rubric will be used for evaluation:

Part-II Evaluation Rubric

| FYP-LO | Below Average | Average | Good | Excellent | Outstanding | Obtained Marks |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| FYP-LO1:Marks(10): Demonstrate knowledge of mathematics, science, and software engineering fundamentals and processes. | Poor understanding of basic software engineering concepts. (0-4 Marks) | Understanding of basic software engineering is satisfactory. (5 Marks) | Good understanding of basic software engineering. (7 Marks) | Excellent understanding of basic software engineering. (8 Marks) | Outstanding understanding of basic software engineering. (10 Marks) |  |  |
| FYP-LO2:Marks(10): Analyze a problem, identify and define software requirements appropriate to its solution. | Lack of appropriate requirements and Market survey is not aligned to project scope. (0-4 Marks) | Requirements are partially aligned with project scope and market survey is aligned to project scope. (5 Marks) | Requirements are gathered through appropriate elicitation techniques and market survey is aligned to project scope. (7 Marks) | Excellent requirement elicitation techniques and market survey is aligned to project scope. (8 Marks) | Outstanding requirement elicitation techniques market survey is 100% aligned to project scope. (10 Marks) |  |  |
| FYP-LO3:Marks(10): Design and implement software engineering solutions for complex problems, components or processes to meet desired needs. | Designs, plans and proposed project is not according to requirements. (0-4 Marks) | Designs, plans and proposed project is alligened with the requirements. (5 Marks) | Designs, plans and proposed project is good and alligened with the requirements. (7 Marks) | Excellent designs, plans and proposed project is according to requirements. (8 Marks) | Outstanding designs, plans and proposed project is according to requirements. (10 Marks) |  |  |
| FYP-LO4:Marks(20): Evaluate a software engineering solution in a methodical way design and, conduct experiments, analyze and interpret experimental data, and synthesize information to derive valid conclusions. | Software Quality Engineering and GUI standards are poorly applied. (0-8 Marks) | Software Quality Engineering and GUI standards implementation is satisfactory. (10 Marks) | Software Quality Engineering and GUI standards applied are good. (14 Marks) | Software Quality Engineering and GUI standards are excellentlty applied. (16 Marks) | Software Quality Engineering and GUI standards are ourstandingly applied. (20 Marks) |  |  |
| FYP-LO5:Marks(15) : Apply appropriate techniques, resources, and modern software engineering tools to solve complex problems. | Poor techniques and no appropriate tools are used. (0-7 Marks) | Techniques are partially satisfactory but no tools are used. (8 Marks) | Good techniques are applied and tools are not appropriate. (11 Marks) | Techniques and tools are used excellently. (13 Marks) | Techniques and tools are used outstandingly. (15 Marks) |  |  |
| FYP-LO6:Marks(15): Work effectively in a team to accomplish a goal. | Poor team work. (0-7 Marks) | Team Work is satisfactory. (8 Marks) | Good team work. (11 Marks) | Excellent team work. (13 Marks) | Outstanding team work. (15 Marks) |  |  |
| FYP-LO7:Marks(10): Communicate effectively on complex engineering activities and make effective presentations. | Poor communication skills. (0-4 Marks) | Communication skills are satisfactorry. (5 Marks) | Good communication skills. (7 Marks) | Excellent communication skills. (8 Marks) | Outstanding communication skills. (10 Marks) |  |  |
| FYP-LO8:Marks(10): Demonstrate knowledge of project management principles and techniques. | Poor knowledge of project management principles and techniques. (0-4 Marks) | Knowledge of project management principles and techniques is satisfactory. (5 Marks) | Good knowledge of project management principles and techniques. (7 Marks) | Excellent knowledge of project management principles and techniques. (8 Marks) | Outstanding knowledge of project management principles and techniques. (10 Marks) |  |  |
| Obtained Marks:______/100 |  |  |  |  |  |  |  |

Evaluation Method:

- 50% by Exam Committee Average + 50% by Supervisor

- Supervisor may evaluate each member of the project group individually

- Decision of the Exam Committee and Supervisor will be final.

For Example:

- Average Marks by Faculty for the Group: 68 (34 %)

- Supervisor Marks for Student 1: 76 (38%)

- Supervisor Marks for Student 2: 60 (30%)

- Supervisor Marks for Student 3: 92 (46%)

- Student 1 Grade: 34+38 = 72% (B Grade)

- Student 2 Grade: 34+30 = 64% (C Grade)

- Student 3 Grade: 34+46 = 80% (A Grade)

Tip: Important things that Exam Committee may thoroughly check during the exam:

- Functional & Non-Functional Requirements

- ERD & Class Diagrams

- Code

- Walkthrough of the Core Component(s)

- Documentation (Formatting and Completeness)

7. Schedule & Milestones

7.1. Final Year Project (Part I)

| Deadline | Milestone | Submit To | Notes / Actions / Deliverables |
| --- | --- | --- | --- |
| Week 1 | Attend Orientation Seminar. | Project Coordinator | - Submit Project Team List (Both SOFT & HARD COPY - Use Template-01) |
| Week 2 | Develop Project Ideas; Find a Supervisor | Project Coordinator | - Submit Initial Proposal (HARD COPY - Use Template-02) |
| Week 4 | Proposal Presentation | Entire Faculty | - Project Proposal Presentation (SOFT COPY - Use Template-03) |
| Week 6 | Finalize Project Proposal | Project Coordinator | - Submit Project Proposal & Plan (Both SOFT & HARD COPY - Use Template-04) |
| Week 15 | Open House | Industry, Faculty & Students | - Banners, Posters, Brochure, Story Board, Prototype, Project Report |
| Week Immediately after Finals | Progress Presentation / Assessment | Exam Committee / Supervisor | - Presentation (Use Template-07), Prototype, Project Report (SOFT COPY - First 5 Chapters – Use Template-05) |

7.2. Final Year Project (Part II)

| Deadline | Milestone | Submit To | Notes / Actions / Deliverables |
| --- | --- | --- | --- |
| Week 13 | Submit Report | Project Coordinator | - Complete Project Report (SOFT COPY - Use Template-05) |
| Week 14 | Final Demo / Assessment | Exam Committee / Supervisor | - Final Presentation (Use Template-06) - Report (Use Template-05) - Full Working Demo |
| Week 15 | Open House | Industry, Faculty & Students | - Banners, Posters, Brochure, Story Board, Prototype, Project Report, Complete Software System |
| Week Immediately After Finals | Submit Project | Project Coordinator | - Documentation (Hard Binding – 3 Copies) - CD (Including Software – Source Code, Appendix in PDF Format) |

8. Policies

8.1. Registration Criteria

You can register in FYP if you have completed at-least 100 credit hours and are not under probation for low CGPA.

8.2. Meetings with Supervisor

All FYP groups are expected to meet with their supervisor once a week to discuss their project progress. For that purpose, the students should maintain their project log file, to make record of their regular meetings. Your supervisor has the rights to assign “F” grade:

- To all group members if group skips three consecutive meetings.

- To individual group members if they fail to attend 75% of the meetings.

Student must submit monthly attendance status (Template-08) to the coordinator. See Section 9 for details.

8.2.1 Supervisor Review Before Presentation

It is mandatory all FYP student to meet and request their supervisor to review various deliverables due before all the presentations:

- You must state in the beginning of your presentations, whether deliverables (including your presentation) were reviewed by your supervisor or not.

8.3. Plagiarism

Any piece of code, framework or component developed by someone else that you are using in your project must be properly acknowledged / referenced in your documentation.  You cannot claim any such code, framework or component as your own.  Your efforts will be evaluated by the amount of work you have done yourself. You must write your own documentation and cannot copy from any other source.

In case a group is found to be involved in plagiarism, all group members will automatically earn “F” grade.

8.4. Group Size

FYP is a group activity, and a team consisting of 3 students is highly encouraged.  Groups consisting of 2, 4 or 5 students can also be formed, only if the scope and complexity of the project justifies these numbers.

8.5. Open House

All students enrolled in FYP (Part 01) and all students enrolled and approved by faculty in FYP (Part 02) are required to participate in the Open House and showcase their projects. Failure to participate will earn them “F” grade; unless they have prior approval from their supervisor and the project coordinator.

8.6. Other Policies

- Number of Group Members: See Section 3.1

- Assessments: See Chapter 6

- Schedule & Milestones: See Chapter 7

9. Responsibilities of Project Students

Success & effectiveness of FYP process depends on how everyone involved play their role. It is therefore important that you clearly understand your responsibilities in this course. Project students must:

- Take full responsibility for their project work

- Ensure that satisfactory progress is made

- Submit work (reports, proposals, plans, presentations) in a specified time

- Ensure that they are familiar with academic rules, regulations and policies

- Ensure that they consult with their supervisor on regular basis

- Prepare periodic progress reports on the project

  - Submit monthly meeting attendance status via provided template signed by supervisor.

- Accept   responsibility   for   confirmation   of   project scope, presentations, and demos

- Keep themselves up-to-date with the project documents/information on VLE

- Familiarize themselves with various milestones, deliverables and schedule of FYP

- Keep supervisors informed on their project activities, progress and problems

- Meet and request their supervisor to review various deliverables due before all the presentations (See Section 8.2.1)

- Ensure that they have sufficient time available each week to work on their project

- Ask for project coordinator’s help, in case of serious problems with the supervisor

- Contact project coordinator on administration issues (including: enrolment, assessment, schedule of key dates, open house, etc.)

- Consult their supervisor on technical issues (including scope of work, extension to projects, theoretical technical questions, resources, project management, etc.)

It is also very important to realize that your supervisor is not your project manager or team lead.  A project supervisor is only expected to:

- Help/Advise students finalize their project proposal

- Advise students on any changes in project that are required by the faculty

- Make time available for regular meetings with students

- Give suggestions, comments on project progress

- Oversee the administration of project and help students from time to time to identify the direction that the project should take. Also, review the monthly meeting progress and give consent to the students.

- Give students reasonable assistance in obtaining access to advice, material and resources with which to carry out the project

- Give students reasonable advice on documenting and presenting the project

- Evaluate and grade students and submit their marks to Project Coordinator

The project coordinator is responsible for overall administration (with assistance from in-charge program and program coordinator) of the FYP process:

- Assist students in understanding the project process (seminar, handbook, VLE)

- Ensure faculty participation (supervisory and non-supervisory) in the process

- Ensure all project groups have been assigned a supervisor

- Ensure the submission of project ideas from students with supervisor signature in the sixth semester

- Collect proposals, reports, attendance status, presentation from students at specified time

- Help resolve problems between students and supervisor

- Ensure the submission of supervisor consent form before the schedule of Final Year Project presentation. (In 12th Week for Part-II and in 15th for Week Part-I)

- Organize all FYP related activities (presentations, open house, external exams)

- Maintain record of faculty project load

- Communicate event dates/schedule to students & faculty members

- Collect semester grades from supervisors & exam committees

- Compile results from evaluation and communicate results to students

10. Appendices

- Template-01: Project Team

- Template-02: Initial Proposal

- Template-03: Proposal Presentation

- Template-04: Proposal & Plan

- Template-05: Project Report

- Template-06: Final Presentation

- Template-07: Progress Presentation

- Template-08: Attendance Status

Template-01: Project Team

Microsoft Word Format

Template-02: Initial Proposal

Microsoft Word Format

Template-03: Proposal Presentation

Microsoft PowerPoint Format

Template-04: Proposal & Plan

Microsoft Word Format

Template-05: Project Report

Microsoft Word Format

Template-06: Final Presentation

Microsoft PowerPoint Format

Template-07: Progress Presentation

Microsoft PowerPoint Format

Template-08: Attendance Status

Microsoft PowerPoint Format

| FYP-LO | Below Average | Average | Good (70%) | Excellent (80%) | Outstanding (100%) | Obtained Marks |
| --- | --- | --- | --- | --- | --- | --- |
| FYP-LO1:Marks(10): Demonstrate knowledge of mathematics, science, and software engineering fundamentals and processes. | Poor understanding of basic software engineering concepts. (0-4 Marks) | Understanding of basic software engineering is satisfactory. (5 Marks) | Good understanding of basic software engineering. (7 Marks) | Excellent understanding of basic software engineering. (8 Marks) | Outstanding understanding of basic software engineering. (10 Marks) |  |
| FYP-LO2:Marks(20): Analyze a problem, identify and define software requirements appropriate to its solution. | Lack of appropriate requirements and Market survey is not aligned to project scope. (0-8 Marks) | Requirements are partially aligned with project scope and market survey is aligned to project scope. (10 Marks) | Requirements are gathered through appropriate elicitation techniques and market survey is aligned to project scope. (14 Marks) | Excellent requirement elicitation techniques and market survey is aligned to project scope. (16 Marks) | Outstanding requirement elicitation techniques market survey is 100% aligned to project scope. (20 Marks) |  |
| FYP-LO3:Marks(20): Design and implement software engineering solutions for complex problems, components or processes to meet desired needs. | Designs, plans and proposed project is not according to requirements. (0-8 Marks) | Designs, plans and proposed project is alligened with the requirements. (10 Marks) | Designs, plans and proposed project is good and alligened with the requirements. (14 Marks) | Excellent Designs, plans and proposed project is according to requirements. (16 Marks) | Outstanding Designs, plans and proposed project is according to requirements. (20 Marks) |  |
| FYP-LO4:Marks(10): Evaluate a software engineering solution in a methodical way design and, conduct experiments, analyze and interpret experimental data, and synthesize information to derive valid conclusions. | Software Quality Engineering and GUI standards are poorly applied. (0-4 Marks) | Software Quality Engineering and GUI standards implementation is satisfactory. (5 Marks) | Software Quality Engineering and GUI standards applied are good. (7 Marks) | Software Quality Engineering and GUI standards are excellentlty applied. (8 Marks) | Software Quality Engineering and GUI standards are ourstandingly applied. (10 Marks) |  |
| FYP-LO5:Marks(10) : Apply appropriate techniques, resources, and modern software engineering tools to solve complex problems. | Poor techniques and no appropriate tools are used. (0-4 Marks) | Techniques are partially satisfactory but no tools are used. (5 Marks) | Good techniques are applied and tools are not appropriate. (7 Marks) | Techniques and tools are used excellently. (8 Marks) | Techniques and tools are used outstandingly. (10 Marks) |  |
| FYP-LO6:Marks(10): Work effectively in a team to accomplish a goal. | Poor team work. (0-4 Marks) | Team Work is satisfactory. (5 Marks) | Good team work. (7 Marks) | Excellent team work. (8 Marks) | Outstanding team working. (10 Marks) |  |
| FYP-LO7:Marks(10): Communicate effectively on complex engineering activities and make effective presentations. | Poor communication skills. (0-4 Marks) | Communication skills are satisfactorry. (5 Marks) | Good communication skills. (7 Marks) | Excellent communication skills. (8 Marks) | Outstanding communication skills. (10 Marks) |  |
| FYP-LO8:Marks(10): Demonstrate knowledge of project management principles and techniques. | Poor knowledge of project management principles and techniques. (0-4 Marks) | Knowledge of project management principles and techniques is satisfactory. (5 Marks) | Good knowledge of project management principles and techniques. (7 Marks) | Excellent knowledge of project management principles and techniques. (8 Marks) | Outstanding knowledge of project management principles and techniques. (10 Marks) |  |

FYP Part 2 Evaluation Rubric

| FYP-LO | Below Average | Average | Good | Excellent | Outstanding | Obtained Marks |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| FYP-LO1:Marks(10): Demonstrate knowledge of mathematics, science, and software engineering fundamentals and processes. | Poor understanding of basic software engineering concepts. (0-4 Marks) | Understanding of basic software engineering is satisfactory. (5 Marks) | Good understanding of basic software engineering. (7 Marks) | Excellent understanding of basic software engineering. (8 Marks) | Outstanding understanding of basic software engineering. (10 Marks) |  |  |
| FYP-LO2:Marks(10): Analyze a problem, identify and define software requirements appropriate to its solution. | Lack of appropriate requirements and Market survey is not aligned to project scope. (0-4 Marks) | Requirements are partially aligned with project scope and market survey is aligned to project scope. (5 Marks) | Requirements are gathered through appropriate elicitation techniques and market survey is aligned to project scope. (7 Marks) | Excellent requirement elicitation techniques and market survey is aligned to project scope. (8 Marks) | Outstanding requirement elicitation techniques market survey is 100% aligned to project scope. (10 Marks) |  |  |
| FYP-LO3:Marks(10): Design and implement software engineering solutions for complex problems, components or processes to meet desired needs. | Designs, plans and proposed project is not according to requirements. (0-4 Marks) | Designs, plans and proposed project is alligened with the requirements. (5 Marks) | Designs, plans and proposed project is good and alligened with the requirements. (7 Marks) | Excellent designs, plans and proposed project is according to requirements. (8 Marks) | Outstanding designs, plans and proposed project is according to requirements. (10 Marks) |  |  |
| FYP-LO4:Marks(20): Evaluate a software engineering solution in a methodical way design and, conduct experiments, analyze and interpret experimental data, and synthesize information to derive valid conclusions. | Software Quality Engineering and GUI standards are poorly applied. (0-8 Marks) | Software Quality Engineering and GUI standards implementation is satisfactory. (10 Marks) | Software Quality Engineering and GUI standards applied are good. (14 Marks) | Software Quality Engineering and GUI standards are excellentlty applied. (16 Marks) | Software Quality Engineering and GUI standards are ourstandingly applied. (20 Marks) |  |  |
| FYP-LO5:Marks(15) : Apply appropriate techniques, resources, and modern software engineering tools to solve complex problems. | Poor techniques and no appropriate tools are used. (0-7 Marks) | Techniques are partially satisfactory but no tools are used. (8 Marks) | Good techniques are applied and tools are not appropriate. (11 Marks) | Techniques and tools are used excellently. (13 Marks) | Techniques and tools are used outstandingly. (15 Marks) |  |  |
| FYP-LO6:Marks(15): Work effectively in a team to accomplish a goal. | Poor team work. (0-7 Marks) | Team Work is satisfactory. (8 Marks) | Good team work. (11 Marks) | Excellent team work. (13 Marks) | Outstanding team work. (15 Marks) |  |  |
| FYP-LO7:Marks(10): Communicate effectively on complex engineering activities and make effective presentations. | Poor communication skills. (0-4 Marks) | Communication skills are satisfactorry. (5 Marks) | Good communication skills. (7 Marks) | Excellent communication skills. (8 Marks) | Outstanding communication skills. (10 Marks) |  |  |
| FYP-LO8:Marks(10): Demonstrate knowledge of project management principles and techniques. | Poor knowledge of project management principles and techniques. (0-4 Marks) | Knowledge of project management principles and techniques is satisfactory. (5 Marks) | Good knowledge of project management principles and techniques. (7 Marks) | Excellent knowledge of project management principles and techniques. (8 Marks) | Outstanding knowledge of project management principles and techniques. (10 Marks) |  |  |
| Obtained Marks:______/100 |  |  |  |  |  |  |  |